## Project Header
Project Name | Mobile Banking Application
Client/Sponsor | Internal Development
Project Manager | Your Name
Budget Prepared By | Your Name
Date Prepared | 2025-08-03
Budget Period | 12 months
Currency | USD

## Executive Summary
Category | Amount | % of Total
Total Development Cost | $
Total Project Cost | $
Contingency Reserve | $
Final Budget | $ | 100%

## Personnel Costs
Role | FTE | Months | Rate/Month | Total Cost
Project Manager | 1 | 12 | 18000 | 216000
Technical Lead | 1 | 10 | 17000 | 170000
Senior Developer | 2 | 10 | 15000 | 300000
Mid Developer | 2 | 12 | 12000 | 288000
Junior Developer | 1 | 8 | 8000 | 64000
QA Engineer | 1 | 8 | 11000 | 88000
UI/UX Designer | 1 | 6 | 13000 | 78000
DevOps Engineer | 0.5 | 12 | 16000 | 96000
Business Analyst | 0.5 | 4 | 14000 | 28000
Total Personnel |  |  |  | 1328000

## Technology Costs
Item | Quantity | Unit Cost | Duration | Total Cost
Development Licenses | 8 | 500 | 12 months | 48000
Testing Tools | 3 | 2000 | 12 months | 72000
Cloud Infrastructure | 1 | 1500 | 12 months | 18000
Security Tools | 1 | 5000 | 12 months | 60000
Mobile Testing Devices | 10 | 800 | One-time | 8000
Servers & Hardware | 1 | 15000 | One-time | 15000
Total Technology |  |  |  | 221000

## Third-Party Services
Service | Description | Amount | Total Cost
Security Audit | Penetration testing | 25000 | 25000
Legal Review | Compliance review | 15000 | 15000
Consulting | Architecture review | 30000 | 30000
Training | Team skill development | 20000 | 20000
Total Services |  |  | 90000

## Operational Costs
Category | Monthly Cost | Months | Total Cost
Office Space | 8 people × $500 = $4000 | 12 | 48000
Utilities & Internet | 1500 | 12 | 18000
Communications | 800 | 12 | 9600
Office Supplies | 400 | 12 | 4800
Total Operational |  |  | 80400

## Travel & Training
Category | Budget | Total Cost
Conference Attendance | 15000 | 15000
Training Courses | 25000 | 25000
Team Building | 5000 | 5000
Client Meetings | 10000 | 10000
Total Travel/Training |  | 55000