## Basic COCOMO Parameters
Project Type | a | b | c | d | Description
Organic | 2.4 | 1.05 | 2.5 | 0.38 | Small teams familiar with requirements
Semi-detached | 3 | 1.12 | 2.5 | 0.35 | Medium teams mixed experience
Embedded | 3.6 | 1.2 | 2.5 | 0.32 | Complex systems tight constraints

## Project Input Section
Parameter | Value | Notes
Project Size (KSLOC) | 25 | Enter size in thousands of lines of code
Project Type | Semi-detached | Select from dropdown: Organic/Semi-detached/Embedded
Calibration Constant (a) | 3 | Auto-populated based on project type
Scale Factor (b) | 1.12 | Auto-populated based on project type
Duration Constant (c) | 2.5 | Auto-populated based on project type
Duration Exponent (d) | 0.35 | Auto-populated based on project type

## Multiplier Lookup
Factor | Very Low | Low | Normal | High | Very High | Extra High
Product Complexity | 0.7 | 0.85 | 1 | 1.15 | 1.3 | 1.65
Team Experience | 1.4 | 1.2 | 1 | 0.85 | 0.7 | 0.5
Development Tools | 1.3 | 1.15 | 1 | 0.9 | 0.82 | 0.7
Time Constraints | 1.6 | 1.3 | 1 | 1 | - | -
Factor | Very Low | Low | Nominal | High | Very High | Extra High
Product Complexity | Very simple logic | Below average logic | Normal complexity | Advanced logic | Complex systems | Mission critical
Team Experience | Novice team | Some experience | Moderate experience | Skilled team | Highly experienced | World-class team
Development Tools | Basic tools only | Limited IDE features | Standard toolchain | Enhanced toolchain | Premium tools | AI-assisted tools
Time Constraints | Relaxed deadlines | Generous timeline | Normal schedule | Slightly rushed | — | —
Risk Factor | Low | Medium | High
Technology Risk | 0.9 | 1 | 1.2
Team Risk | 0.8 | 1 | 1.3
Requirements Risk | 0.9 | 1 | 1.4
Integration Risk | 0.8 | 1 | 1.5

## Effort Multipliers
Factor | Rating | Multiplier | Description
Product Complexity | Normal | 1 | Normal complexity
Team Experience | High | 0.85 | Skilled team
Development Tools | High | 0.9 | Enhanced toolchain
Time Constraints | Normal | 1 | Normal schedule
Combined Multiplier |  | 0.765 | Product of all multipliers

## Calculations
Calculation | Formula | Value | Units
Base Effort | a * (size^b) | 110.3606 | Person-months
Adjusted Effort | Base * Combined Multiplier | 84.4259 | Person-months
Effort in Hours | Adjusted Effort * 152 | 12832.7309 | Hours
Duration (months) | c * (Effort^d) | 11.8088 | Months
Team Size | Effort / Duration | 7.1494 | People

## Results Summary
Metric | Value | Range
Estimated Effort | 85 | Person-months
Project Duration | 12 | Months
Recommended Team Size | 8 | People
Confidence Level | Medium | Based on project characteristics

## Additional Factors
Risk Factor | Selected | Multiplier
Technology Risk | Medium | 1
Team Risk | Medium | 1
Requirements Risk | Medium | 1
Integration Risk | Medium | 1

## Final Adjusted Estimate
Rate per PM | 15000 | Adjust value if you have cost per PM
Metric | Value | Units
Base Estimate | 85 | Person-Months
Risk Adjustment | 1
Final Estimate | 85 | Person-Months
Contingency (15%) | 12.75 | Person-Months
Project Budget | 97.75
Duration | 13 | Months
Team Size | 8 | People
Cost Estimate | 1466250
Notes:
Team Level | Typical Rate/PM (MYR) |  | Notes
Junior Developer | RM 8,000 – RM 12,000 |  | Entry-level, fresh grads, etc.
Mid-Level Developer | RM 12,000 – RM 18,000 |  | 2–5 years of experience
Senior Developer | RM 18,000 – RM 25,000 |  | Includes some system design, mentoring responsibilities
Team Lead / Architect | RM 25,000 – RM 35,000 |  | Strong leadership, system design, planning
External Consultant | RM 35,000 – RM 50,000+ |  | High-end consultants, niche roles, or short-term expertise