## Project Information
Project Information
Project Name | E-commerce Web Application
Project Manager | Your Name
Estimation Date | 2025-08-03
Project Duration (weeks) | 12
Total Effort (hours) | 4320
Notes and Assumptions
1. Rates are based on current market rates in your region
2. Utilization factors account for non-billable time
3. Indirect costs include typical organizational overhead
4. Contingency is based on risk assessment
5. Update actuals regularly for project control

## Team Structure and Rates
Team Structure and Rates
Role | Count | Rate ($/hour) | Utilization % | Effective Rate
Project Manager | 1 | 90 | 100% | 90
Senior Developer | 2 | 85 | 95% | 80.75
Mid-level Developer | 2 | 65 | 90% | 58.5
Junior Developer | 1 | 45 | 85% | 38.25
QA Engineer | 1 | 60 | 90% | 54
UI/UX Designer | 1 | 70 | 75% | 52.5
DevOps Engineer | 1 | 80 | 60% | 48

## Effort Distribution By Role
Effort Distribution by Role
Role | Total Hours | Cost Calculation
Project Manager | 480 | 43200
Senior Developer | 1728 | 139536
Mid-level Developer | 1512 | 88452
Junior Developer | 648 | 24786
QA Engineer | 1080 | 58320
UI/UX Designer | 240 | 12600
DevOps Engineer | 180 | 8640
Subtotal Direct Labor |  | 375534

## Indirect Costs
Indirect Costs
Cost Category | Calculation Method | Rate/Amount | Total Cost
Benefits & Payroll Taxes | % of Direct Labor | 25% | 93883.5
Equipment & Software | Per Person | 1500 | 13500
Office Space & Utilities | Per Person Per Month | 500 | 13500
Management Overhead | % of Direct Costs | 20% | 75106.8
Administrative Overhead | % of Direct Costs | 15% | 56330.1
Subtotal Indirect Costs |  |  | 252320.4

## Risk Assessment
Risk Assessment and Contingency
Risk Factor | Probability | Impact | Score | Weight
Technology Risk | 30% | High | 3 | 1.2
Team Risk | 20% | Medium | 2 | 1.1
Requirements Risk | 40% | Medium | 2 | 1.15
Integration Risk | 25% | High | 3 | 1.1
Schedule Risk | 35% | Medium | 2 | 1.08
Combined Risk Multiplier |  |  |  | 1.6698

## Project Budget Summary
Project Budget Summary
Component | Amount | Percentage
Direct Labor Costs | 375534
Indirect Costs | 252320.4
Subtotal Project Costs | 627854.4 | 85%
Risk Contingency (15%) | 94178.16 | 15%
Total Project Budget | 722032.56 | 100%

## Budget by Phase
Budget by Phase
Phase | Duration (weeks) | Effort % | Labor Cost | Total Cost
Planning & Design | 2 | 20% | 75106.8 | 144406.512
Development | 6 | 55% | 206543.7 | 397117.908
Testing | 3 | 20% | 75106.8 | 144406.512
Deployment | 1 | 5% | 18776.7 | 36101.628
Total | 12 | 100% | 375534 | 722032.56

## Cost Control Metrics
Cost Control Metrics
Metric | Target | Actual | Variance
Budget Variance | 0% | TBD | TBD
Schedule Variance | 0% | TBD | TBD
Resource Utilization | 90% | TBD | TBD
Cost per Hour | $ | TBD | TBD

## Monthly Cash Flow
Monthly Cash Flow
Month | Planned Spend | Cumulative Spend | Budget %
Month 1
Month 2
Month 3
Total |  |  | 100%