## Project Information
Project Name | E-learning Platform Development
Analysis Date | 2025-08-03
Analyst | Your Name
Project Duration Target | 16 weeks

## Task Network Definition
Task ID | Task Name | Duration (days) | Depends On | Resource | Notes | Successors
A | Requirements Analysis | 10 |  | BA | Gather and document requirements | B
B | System Architecture | 5 | A | Architect | Design system architecture | E,F
C | Database Design | 7 | A | DB Designer | Database schema and design | G
D | UI Design | 15 | A | UI Designer | User interface mockups | H,J
E | Dev Environment Setup | 3 | B | DevOps | Development tools and CI/CD | F
F | Authentication Module | 12 | B+E | Sr Dev 1 | User login and security | G,H,J
G | Content Management | 20 | F+C | Sr Dev 2 | Course and content management | I,K
H | Student Portal | 15 | F+D | Mid Dev 1 | Student interface development | I,K
I | Assessment System | 18 | G+H | Sr Dev 1 | Quizzes and grading system | K
J | Discussion Forums | 10 | F+D | Mid Dev 2 | Communication features | K
K | Integration Testing | 10 | G+H+I+J | QA Team | System integration tests | L
L | Performance Testing | 5 | K | QA Lead | Load and performance tests | M
M | User Acceptance | 7 | L | Business Users | Final user testing | N
N | Deployment | 3 | M | DevOps | Production deployment

## ForwardBackward
Task | Task Name | Duration (days) | Depends On | Successors | Early Start (ES) | Early Finish (EF) | Late Start (LS) | Late Finish (LF) | Float | Critical? | ProjectFinish

## Resource Loading Analysis
Week | BA | Architect | Designer | Sr Dev 1 | Sr Dev 2 | Mid Dev 1 | Mid Dev 2 | QA | DevOps
1-2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
4-6 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1
7-10 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0
11-14 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0
15-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
17-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1

## Resource Conflicts Analysis
Week | Resource | Demand | Available | Conflict? | Resolution
4 | Sr Dev 1 | 1 | 1 | No
7 | All Devs | 4 | 3 | Yes | Adjust schedule or add resource
11 | Sr Dev 1 | 1 | 1 | No
14 | QA Team | 1 | 1 | No

## Schedule Optimization Options
Option | Description | Time Saved | Cost Impact | Risk Level
Fast Track 1 | Overlap UI Design with Architecture | 2 weeks | Low | Medium
Fast Track 2 | Start Development with partial requirements | 3 weeks | Medium | High
Crash 1 | Add additional developer | 4 weeks | High | Low
Crash 2 | Add QA resources for parallel testing | 1 week | Medium | Low
Scope Reduce | Move forums to Phase 2 | 2 weeks | Low | Low

## What-If Scenarios
Scenario | Changes | New Duration | Impact
Baseline | No changes | 18.6 weeks
Optimistic | All fast tracking + crash | 12 weeks | + $50K cost; High risk
Realistic | Selected fast track + scope | 15 weeks | + $15K cost; Medium risk
Pessimistic | Resource delays | 22 weeks | Schedule slip

## Critical Path Monitoring
Task | Baseline Duration | Current Estimate | Variance | Impact on Project
A - Requirements | 10 days | 10 days | 0 | None
B - Architecture | 5 days | 7 days | +2 days | +2 days to project
E - Dev Setup | 3 days | 3 days | 0 | None
F - Authentication | 12 days | 15 days | +3 days | +3 days to project
G - Content Mgmt | 20 days | 20 days | 0 | None

## Risk Impact on Critical Path
Risk Event | Probability | Impact on CP | Mitigation | Contingency
Key developer leaves | 20% | +3 weeks | Cross-training | Contractor ready
Requirements change | 30% | +2 weeks | Change control | Buffer time
Technology issues | 15% | +1 week | Proof of concept | Alternative tech
Integration problems | 25% | +1 week | Early integration | Extra QA time

## Schedule Compression Analysis
Critical Task | Normal Duration | Crash Duration | Crash Cost | Cost/Day Saved
F - Authentication | 12 days | 8 days | $8000 | $2000
G - Content Mgmt | 20 days | 15 days | $15000 | $3000
I - Assessment | 18 days | 12 days | $18000 | $3000
K - Integration | 10 days | 7 days | $6000 | $2000

## Float Management
Task with Float | Float Days | Management Strategy
C - Database Design | 13 | Resource leveling opportunity
D - UI Design | 5 | Monitor closely - near critical
H - Student Portal | 5 | Monitor closely - near critical
J - Discussion Forums | 28 | Delay if needed for resources

## Project Control Metrics
Metric | Target | Current | Status
Schedule Performance Index (SPI) | 1 | TBD | TBD
Critical Path Progress | % | TBD | TBD
Float Consumption | 0 days | TBD | TBD
Resource Utilization | 85% | TBD | TBD

## Action Items
Priority | Action | Owner | Due Date | Status
High | Confirm resource availability | PM | Weekly | Ongoing
High | Monitor critical path tasks | PM | Daily | Ongoing
Medium | Plan resource leveling | PM | Week 2 | Pending
Medium | Prepare crash options | PM | Week 3 | Pending
Low | Update stakeholders | PM | Weekly | Ongoing

## Reporting Schedule
Report | Frequency | Recipients | Content
Critical Path Status | Weekly | Stakeholders | Progress and issues
Schedule Dashboard | Daily | Team | Task completion status
Milestone Report | Monthly | Management | Major deliverables
Risk Assessment | Bi-weekly | PM + Sponsor | Schedule risks

## Notes and Assumptions
Note # | Assumption
1 | Durations are in working days (5 days/week)
2 | Resource availability confirmed with managers
3 | Dependencies are firm finish-to-start relationships
4 | Critical path analysis updated weekly
5 | Float calculations assume no resource constraints
6 | Crash costs include overtime and additional resources
7 | Risk probabilities based on historical data
8 | Buffer time not included in critical path calculation