## Project Info
Project Name | Mobile Banking Application
Project Manager | Your Name
Start Date | 2025-09-01
Target End Date | 2025-12-15
Status Date | 2025-08-03
Baseline Date | TBD

## WBS
WBS | Task Name | Duration | Start | Finish | Predecessors | Resource Names | % Complete
1 | Mobile Banking Project | 15 weeks | 2025-09-01 | 2025-12-15 |  | PM | 0%
1.1 | Project Initiation | 2 weeks | 2025-09-01 | 2025-09-12 |  | PM+BA | 0%
1.1.1 | Requirements Gathering | 2 weeks | 2025-09-01 | 2025-09-12 |  | BA+PM | 0%
1.1.2 | Stakeholder Analysis | 1 week | 2025-09-01 | 2025-09-05 | 1.1.1 | BA | 0%
1.1.3 | Project Charter | 1 week | 2025-09-08 | 2025-09-12 | 1.1.1 | PM | 0%
1.2 | Analysis & Design | 3 weeks | 2025-09-15 | 2025-10-03 | 1.1 | Architect+Designer | 0%
1.2.1 | System Architecture | 2 weeks | 2025-09-15 | 2025-09-26 | 1.1.3 | Architect | 0%
1.2.2 | Database Design | 1.5 weeks | 2025-09-22 | 2025-10-01 | 1.2.1 | DB Architect | 0%
1.2.3 | UI/UX Design | 3 weeks | 2025-09-15 | 2025-10-03 | 1.1.1 | UI Designer | 0%
1.2.4 | API Design | 1 week | 2025-09-29 | 2025-10-03 | 1.2.1 | Sr Developer | 0%
1.3 | Development Setup | 1 week | 2025-10-06 | 2025-10-10 | 1.2 | DevOps+Sr Dev | 0%
1.3.1 | Development Environment | 3 days | 2025-10-06 | 2025-10-08 | 1.2.1 | DevOps | 0%
1.3.2 | CI/CD Pipeline | 3 days | 2025-10-08 | 2025-10-10 | 1.3.1 | DevOps | 0%
1.3.3 | Code Repository Setup | 2 days | 2025-10-06 | 2025-10-07 | 1.2.1 | Sr Developer | 0%
1.4 | Core Development | 6 weeks | 2025-10-13 | 2025-11-21 | 1.3 | Dev Team | 0%
1.4.1 | Authentication System | 2 weeks | 2025-10-13 | 2025-10-24 | 1.3.2 | Sr Dev A | 0%
1.4.2 | User Management | 2 weeks | 2025-10-27 | 2025-11-07 | 1.4.1 | Sr Dev B | 0%
1.4.3 | Account Dashboard | 3 weeks | 2025-10-27 | 2025-11-14 | 1.4.1 | Mid Dev A+B | 0%
1.4.4 | Transaction Processing | 3 weeks | 2025-11-03 | 2025-11-21 | 1.4.2 | Sr Dev A | 0%
1.4.5 | Payment Integration | 2 weeks | 2025-11-10 | 2025-11-21 | 1.4.4 | Sr Dev B | 0%
1.4.6 | Mobile App Framework | 4 weeks | 2025-10-20 | 2025-11-14 | 1.2.3 | Mobile Dev | 0%
1.4.7 | API Implementation | 4 weeks | 2025-10-20 | 2025-11-14 | 1.2.4 | Sr Dev A+B | 0%
1.5 | Testing Phase | 3 weeks | 2025-11-24 | 2025-12-12 | 1.4 | QA Team | 0%
1.5.1 | Unit Testing | Ongoing | 2025-10-13 | 2025-11-21 | 1.4 | Developers | 0%
1.5.2 | Integration Testing | 2 weeks | 2025-11-24 | 2025-12-05 | 1.4.7 | QA Engineer A | 0%
1.5.3 | System Testing | 2 weeks | 2025-11-24 | 2025-12-05 | 1.4 | QA Engineer B | 0%
1.5.4 | Performance Testing | 1 week | 2025-12-01 | 2025-12-05 | 1.5.3 | Performance Tester | 0%
1.5.5 | Security Testing | 1 week | 2025-12-01 | 2025-12-05 | 1.5.3 | Security Tester | 0%
1.5.6 | User Acceptance Testing | 1 week | 2025-12-08 | 2025-12-12 | 1.5.2 | Business Users | 0%
1.6 | Deployment | 1 week | 2025-12-15 | 2025-12-19 | 1.5.6 | DevOps+Support | 0%
1.6.1 | Production Setup | 2 days | 2025-12-15 | 2025-12-16 | 1.5.6 | DevOps | 0%
1.6.2 | Data Migration | 1 day | 2025-12-17 | 2025-12-17 | 1.6.1 | Database Admin | 0%
1.6.3 | Go-Live Support | 3 days | 2025-12-17 | 2025-12-19 | 1.6.2 | Support Team | 0%

## Gantt Chart (hidden)
Task Name | Start | Finish | Critical | Duration (days) | Sep-01 | Sep-02 | Sep-03 | Sep-04 | Sep-05 | Sep-06 | Sep-07 | Sep-08 | Sep-09 | Sep-10 | Sep-11 | Sep-12 | Sep-13 | Sep-14 | Sep-15 | Sep-16 | Sep-17 | Sep-18 | Sep-19 | Sep-20 | Sep-21 | Sep-22 | Sep-23 | Sep-24 | Sep-25 | Sep-26 | Sep-27 | Sep-28 | Sep-29 | Sep-30 | Oct-01 | Oct-02 | Oct-03 | Oct-04 | Oct-05 | Oct-06 | Oct-07 | Oct-08 | Oct-09 | Oct-10 | Oct-11 | Oct-12 | Oct-13 | Oct-14 | Oct-15 | Oct-16 | Oct-17 | Oct-18 | Oct-19 | Oct-20 | Oct-21 | Oct-22 | Oct-23 | Oct-24 | Oct-25 | Oct-26 | Oct-27 | Oct-28 | Oct-29 | Oct-30 | Oct-31 | Nov-01 | Nov-02 | Nov-03 | Nov-04 | Nov-05 | Nov-06 | Nov-07 | Nov-08 | Nov-09 | Nov-10 | Nov-11 | Nov-12 | Nov-13 | Nov-14 | Nov-15 | Nov-16 | Nov-17 | Nov-18 | Nov-19 | Nov-20 | Nov-21 | Nov-22 | Nov-23 | Nov-24 | Nov-25 | Nov-26 | Nov-27 | Nov-28 | Nov-29 | Nov-30 | Dec-01 | Dec-02 | Dec-03 | Dec-04 | Dec-05 | Dec-06 | Dec-07 | Dec-08 | Dec-09 | Dec-10 | Dec-11 | Dec-12 | Dec-13 | Dec-14 | Dec-15 | Dec-16 | Dec-17 | Dec-18 | Dec-19 | Dec-20 | Dec-21 | Dec-22 | Dec-23 | Dec-24 | Dec-25 | Dec-26 | Dec-27 | Dec-28 | Dec-29 | Dec-30 | Dec-31
Mobile Banking Project | 2025-09-01 | 2025-12-15 | No | 106 | bar: Sep-01 to Dec-15
Project Initiation | 2025-09-01 | 2025-09-12 | No | 12 | bar: Sep-01 to Sep-12
Requirements Gathering | 2025-09-01 | 2025-09-12 | Yes | 12 | bar: Sep-01 to Sep-12
Stakeholder Analysis | 2025-09-01 | 2025-09-05 | No | 5 | bar: Sep-01 to Sep-05
Project Charter | 2025-09-08 | 2025-09-12 | No | 5 | bar: Sep-08 to Sep-12
Analysis & Design | 2025-09-15 | 2025-10-03 | No | 19 | bar: Sep-15 to Oct-03
System Architecture | 2025-09-15 | 2025-09-26 | Yes | 12 | bar: Sep-15 to Sep-26
Database Design | 2025-09-22 | 2025-10-01 | No | 10 | bar: Sep-22 to Oct-01
UI/UX Design | 2025-09-15 | 2025-10-03 | No | 19 | bar: Sep-15 to Oct-03
API Design | 2025-09-29 | 2025-10-03 | No | 5 | bar: Sep-29 to Oct-03
Development Setup | 2025-10-06 | 2025-10-10 | Yes | 5 | bar: Oct-06 to Oct-10
Development Environment | 2025-10-06 | 2025-10-08 | No | 3 | bar: Oct-13 to Nov-21
CI/CD Pipeline | 2025-10-08 | 2025-10-10 | No | 3 | bar: Nov-24 to Dec-12
Code Repository Setup | 2025-10-06 | 2025-10-07 | Yes | 2 | bar: Dec-15 to Dec-19
Core Development | 2025-10-13 | 2025-11-21 | No | 40
Authentication System | 2025-10-13 | 2025-10-24 | Yes | 12
User Management | 2025-10-27 | 2025-11-07 | No | 12
Account Dashboard | 2025-10-27 | 2025-11-14 | No | 19
Transaction Processing | 2025-11-03 | 2025-11-21 | Yes | 19
Payment Integration | 2025-11-10 | 2025-11-21 | No | 12
Mobile App Framework | 2025-10-20 | 2025-11-14 | No | 26
API Implementation | 2025-10-20 | 2025-11-14 | No | 26
Testing Phase | 2025-11-24 | 2025-12-12 | No | 19
Unit Testing | 2025-10-13 | 2025-11-21 | No | 40
Integration Testing | 2025-11-24 | 2025-12-05 | Yes | 12
System Testing | 2025-11-24 | 2025-12-05 | No | 12
Performance Testing | 2025-12-01 | 2025-12-05 | No | 5
Security Testing | 2025-12-01 | 2025-12-05 | No | 5
User Acceptance Testing | 2025-12-08 | 2025-12-12 | Yes | 5
Deployment | 2025-12-15 | 2025-12-19 | Yes | 5
Production Setup | 2025-12-15 | 2025-12-16 | No | 2
Data Migration | 2025-12-17 | 2025-12-17 | No | 1
Go-Live Support | 2025-12-17 | 2025-12-19 | No | 3

## Resource Pool
Resource Name | Type | Max Units | Standard Rate | Overtime Rate | Group
PM | Work | 1 | $90/hr | $135/hr | Management
BA | Work | 1 | $75/hr | $113/hr | Analysis
Architect | Work | 1 | $95/hr | $143/hr | Technical
UI Designer | Work | 1 | $70/hr | $105/hr | Design
Sr Developer A | Work | 1 | $85/hr | $128/hr | Development
Sr Developer B | Work | 1 | $85/hr | $128/hr | Development
Mid Dev A | Work | 1 | $65/hr | $98/hr | Development
Mid Dev B | Work | 1 | $65/hr | $98/hr | Development
Mobile Dev | Work | 1 | $80/hr | $120/hr | Development
QA Engineer A | Work | 1 | $60/hr | $90/hr | Testing
QA Engineer B | Work | 1 | $60/hr | $90/hr | Testing
Performance Tester | Work | 0.5 | $70/hr | $105/hr | Testing
Security Tester | Work | 0.25 | $80/hr | $120/hr | Testing
DevOps | Work | 1 | $85/hr | $128/hr | Infrastructure
DB Architect | Work | 0.5 | $90/hr | $135/hr | Technical
Database Admin | Work | 0.25 | $75/hr | $113/hr | Infrastructure
Support Team | Work | 1 | $55/hr | $83/hr | Support

## Milestones
Milestone | Date | Description | Deliverables
Project Kickoff | 2025-09-01 | Project officially starts | Charter approved
Requirements Complete | 2025-09-01 | All requirements gathered | Requirements document
Design Complete | 2025-10-01 | Architecture and UI approved | Design documents
Development Start | 2025-10-01 | Coding begins | Development environment ready
Alpha Release | 2025-11-01 | Core features complete | Working prototype
Code Complete | 2025-11-01 | All development finished | Feature-complete application
Testing Complete | 2025-12-01 | All testing passed | Test reports and sign-off
Go-Live | 2025-12-01 | System in production | Live application

## Resource Loading
Week | PM | Developers | QA | DevOps | Others | Total
Week 1-2 | 40 | 0 | 0 | 0 | 40 | 80
Week 3-5 | 40 | 40 | 0 | 20 | 40 | 140
Week 6 | 40 | 80 | 0 | 40 | 0 | 160
Week 7-12 | 40 | 320 | 0 | 20 | 0 | 380
Week 13-15 | 40 | 80 | 160 | 40 | 20 | 340
Week 16 | 20 | 40 | 40 | 40 | 20 | 160

## Budget by Phase
Phase | Duration | Labor Hours | Labor Cost | Other Costs | Total Cost
Project Initiation | 2 weeks | 160 | $13600 | $2000 | $15600
Analysis & Design | 3 weeks | 280 | $24800 | $5000 | $29800
Development Setup | 1 week | 80 | $7200 | $3000 | $10200
Core Development | 6 weeks | 1440 | $118800 | $10000 | $128800
Testing Phase | 3 weeks | 720 | $45600 | $15000 | $60600
Deployment | 1 week | 120 | $9000 | $5000 | $14000
Total Project | 16 weeks | 2800 | $219000 | $40000 | $259000

## Risk Register
Risk | Probability | Impact | Response | Owner | Status
Requirements changes | High | Medium | Change control process | PM | Open
Key developer unavailable | Medium | High | Cross-training | PM | Open
Third-party API delays | Low | High | Early integration testing | Tech Lead | Open
Performance issues | Medium | Medium | Performance testing | QA Lead | Open
Security vulnerabilities | Low | High | Security review | Security | Open

## Quality Gates
Phase | Entry Criteria | Exit Criteria | Deliverables
Design | Requirements approved | Architecture reviewed | Design documents
Development | Design approved | Code complete + unit tests | Working code
Testing | Code complete | All tests passed | Test reports
Deployment | Testing complete | Production deployment | Live system

## Communication Plan
Stakeholder | Method | Frequency | Information
Sponsor | Status Report | Weekly | Progress and issues
Team | Stand-up | Daily | Task status
Stakeholders | Demo | Bi-weekly | Working software
Management | Dashboard | Weekly | Metrics and KPIs

## Change Control
Change Request | Date | Description | Impact | Status | Approved By
CR001 | TBD | Example change | +2 weeks | Pending | Sponsor
CR002 | TBD | Example change | +$5000 | Pending | PM