## Project Information
Project Name | Customer Portal Web Application
Application Type | Business Web Application
Development Effort (hours) | 3200
Quality Requirements | Standard Business Application
Testing Manager | Your Name
Date | 2025-08-03

## Method 1
Percentage of Development Effort
Application Type | Testing % | Development Hours | Testing Hours
Business Web Apps | 25-35% | 3200 | 960
E-commerce | 30-40% | 3200 | 1120
Financial Systems | 40-50% | 3200 | 1440
Safety-Critical | 50-100% | 3200 | 2400
Selected Type | Business Web Apps | 3200 | 960

## Method 2
Testing by Type
Testing Type | % of Total Testing | Hours | Cost @ $55/hr | Description
Unit Testing | 25% | 240 | 13200 | Developer responsibility
Integration Testing | 20% | 192 | 10560 | API and database testing
System Testing | 30% | 288 | 15840 | End-to-end functionality
User Acceptance Testing | 15% | 144 | 7920 | Business stakeholder testing
Performance Testing | 10% | 96 | 5280 | Load and stress testing
Total Testing Effort | 100% | 960 | 52800

## Method 3
Feature-Based Testing
Feature Area | Complexity | Test Cases | Hours/Case | Total Hours
User Authentication | Medium | 25 | 2 | 50
Customer Dashboard | High | 40 | 2.5 | 100
Order Management | High | 35 | 3 | 105
Payment Processing | High | 30 | 3.5 | 105
Product Catalog | Medium | 45 | 2 | 90
Support System | Low | 20 | 1.5 | 30
Reporting | Medium | 25 | 2.5 | 63
Mobile Interface | High | 35 | 2.5 | 88
Total Features |  |  |  | 631

## Quality Factors
Quality Factors Adjustment
Quality Factor | Target Level | Multiplier | Applied
Functionality | 95% pass rate | 1 | Yes
Reliability | 99% uptime | 1.2 | Yes
Performance | <3 sec response | 1.1 | Yes
Security | Standard protection | 1 | Yes
Usability | Good user experience | 1 | Yes
Combined Multiplier |  | 1.32 | 1.32

## Adjusted Effort
Adjusted Testing Effort
Base Testing Effort | 960 | hours
Quality Multiplier | 1.32
Adjusted Testing Effort | 1267 | 1267.2 | hours
Risk Buffer (10%) | 127 | 126.7 | hours
Final Testing Effort | 1394 | 1394 | hours

## Testing Team
Testing Team Structure
Role | Count | Rate ($/hour) | Utilization | Effective Rate
Test Manager | 1 | 70 | 80% | 56
Senior QA Engineer | 2 | 60 | 90% | 54
Mid-level QA Engineer | 2 | 50 | 90% | 45
Junior QA Engineer | 1 | 35 | 85% | 30
Performance Tester | 1 | 65 | 50% | 33
Security Tester | 1 | 70 | 25% | 18
Average Blended Rate |  |  |  | 48

## Testing Schedule
Testing Schedule Planning
Phase | Duration (weeks) | Effort (hours) | Team Size | Description
Test Planning | 2 | 120 | 2 | Strategy and case design
Test Execution | 6 | 840 | 4 | Execute test cases
Defect Resolution | 3 | 300 | 3 | Fix bugs and retest
Final Validation | 1 | 80 | 2 | Smoke tests and sign-off
Total Test Schedule | 12 | 1340 | Average: 3

## Environment Costs
Test Environment Costs
Environment | Setup Cost | Monthly Cost | Duration | Total Cost
Development | 2000 | 500 | 3 months | 3500
Testing | 5000 | 800 | 4 months | 8200
Staging | 3000 | 600 | 2 months | 4200
Performance | 4000 | 1000 | 1 month | 5000
Total Environment Costs | 14000 | 2900 |  | 20900

## Tools and Licenses
Testing Tools and Licenses
Tool | License Type | Cost | Users | Total Cost
Test Management | Annual | 1200 | 5 | 6000
Automation Tool | Annual | 2000 | 3 | 6000
Performance Tool | Annual | 5000 | 1 | 5000
Security Scanner | Annual | 3000 | 1 | 3000
Mobile Testing | Annual | 1500 | 2 | 3000
Total Tool Costs |  |  |  | 23000

## Defect Estimation
Defect Estimation
Phase | Defects/KLOC | Code Size (KLOC) | Estimated Defects | Fix Time (hrs) | Total Hours
Unit Testing | 8 | 25 | 200 | 1.5 | 300
Integration Testing | 3 | 25 | 75 | 2.5 | 188
System Testing | 2 | 25 | 50 | 3 | 150
UAT | 1 | 25 | 25 | 2 | 50
Total Defects |  |  | 350 |  | 688

## Budget Summary
Testing Budget Summary
Category | Hours | Rate | Cost | % of Total
Testing Team | 1394 | 48 | 66912 | 60%
Test Environment |  |  | 20900 | 19%
Testing Tools |  |  | 23000 | 21%
Total Testing Budget |  |  | 110812 | 100%

## Risk Assessment
Risk Assessment
Risk Factor | Probability | Impact | Mitigation | Contingency
Requirements Changes | High | Medium | Early involvement | 10%
Environment Issues | Medium | High | Early setup | 5%
Tool Problems | Low | Medium | Vendor support | 3%
Resource Availability | Medium | High | Cross-training | 7%
Total Risk Contingency |  |  |  | 25%

## Final Estimate
Final Testing Estimate
Base Testing Cost |  | 110812
Risk Contingency (25%) |  | 27703
Final Testing Budget |  | 138515
Testing as % of Development | 43% | #NAME?

## Quality Metrics
Quality Metrics Targets
Metric | Target | Measurement Method
Test Coverage | 90% | Code coverage tools
Defect Detection Rate | 85% | Defects found in testing / total
Defect Leakage | <5% | Defects found in production
Test Execution Rate | 95% | Tests passed / total tests
Automation Coverage | 60% | Automated tests / total tests

## Reporting Schedule
Reporting Schedule
Report | Frequency | Recipients
Test Progress | Weekly | PM and stakeholders
Defect Summary | Weekly | Development team
Coverage Report | Daily | Test team
Quality Dashboard | Daily | All team members
Final Test Report | End of phase | All stakeholders